## 城
附件3
钦州市2023年市级重大项目推进情况表 （“造滨城”项目）
填报单位：钦州市城市管理行政执法局 | [11 empty] | 单位：万元
序号 | 项目名称 | 建设性质 | 主要建设内容及规模 | 建设起止年限 | 总投资 | 年度 计划投资 （万元） | 自开工以来到2022年底累计完成投资 （万元） | 实际开工/ 竣工月份（新开工、竣工项目填写） | 1-11月完成 投资 （万元） | 目前进展情况 | 存在主要问题和困难 | 项目业主或前期工作责任单位 | 项目负责人及联系电话 | 责任单位
| 合计（6个） |  |  |  | 120637.9 | 15600 | 21206.99 |  | 11594
| （一）主城区基础设施（6个） |  |  |  | 120637.9 | 15600 | 21206.99 |  | 11594
1 | 河西片区雨污分流改造工程 | 续建 | 建设河西片区雨污分流排水管网143公里、雨水检查井42座、污水检查井3067座、一体化提升泵站2座、破除并恢复路面41万平方米、管道清淤3.6万立方米。 | 2017-2024 | 44818 | 3000 | 7895 |  | 3620 | （一）海城片区（海城一巷~海城六巷）雨污分流改造工程：完成海城一巷至海城六巷雨水检查井83座雨水管网1774米，污水检查26座，污水管网665米，完成海城路及海城六巷高压旋喷桩2276根，海城六巷高压摆喷813根,恢复海城一巷至六巷、海城路砼路面1686米。已完工。 （二）海城片区（海城七巷至海城十巷）管网改造工程：已开工建设,目前已完成全部施工内容，正办理规划测量工作。 （三）钦州湾大道东侧非机动车道（文华新城）污水管道修复工程：于2023年2月22日开工建设，已完成污水管道的施工,目前正整理竣工资料，准备办理竣工验收。 （四）英华片区（英华一巷至英华九巷）管网改造工程：已开工建设，目前已完成约1600米的管道施工及路面恢复。 （五）英华片区（英华十巷至英华十六巷）管网改造工程：累计完成552米雨水管敷设施工，完成110米污水管敷设施工，完成562米路面恢复施工。英华十一巷完成176米雨水管敷设，并完成路面恢复施工。完成英华十三巷152米雨水管敷设，并完成路面恢复施工，英华十五巷完完成124米雨水管敷设施工，并完成路面恢复施工。英华十巷完成100米雨水管铺设。 （六）城西片区（建设路与新兴路之间）管网改造工程：已开工建设，已完成约2600米的管道施工及路面恢复。 （七）文峰北路（子材西大街至永福西大街）管网改造工程：未开工，原设计图纸中雨污水管管顶50cm以上至路面结构层底利用开挖原有土方作为回填材料，考虑到该路段为主干道，车流量较多，不能按照设计图纸放坡开挖，如采用原土回填存在较大的质量隐患，且无法满足设计要求的压实度和承载力检测，建议采用中粗砂作为回填材料，增加造价约100万元，已拟文报集团批示。 （八）北部湾大道（环城北路至南珠西大街）东侧污水管道修复工程：已进场施工，目前正进行钢板桩的施工及污水管道的开挖工作，已完成100米的管道施工，钢板桩施工方案还未确定，属于停工状态。 | （一）海城片区（海城一巷~海城六巷）雨污分流改造工程：海城五巷仍有钢板桩未拆除。 （二）文峰北路（子材西大街至永福西大街）管网改造工程：现场部分管网位置设置在绿化范围内，需要设计调整位置。 （三）北部湾大道因钢板桩需要进行引孔，设计单位出具优化方案，已报集团进行审批。 （四）英华片区（英华十巷至英华十六巷）由于资金不到位，目前已停工。 | 钦州市开发投资集团有限公司 | 梁鸿 13471713569 | 市城管执法局
2 | 钦州市城区老旧供水管网改造工程 | 续建 | 改建城区老旧供水管网，管径DN200－DN800mm，管长约28公里；完善城区供水检测系统，设置分区计量设施。 | 2021-2024 | 25628 | 3000 | 6174 |  | 1651 | 完成南珠西大街DN300-DN500管约320米。银河街DN500管约200米。完成文峰路、新华路、宫保街等道路DN100-DN600管约6721米。 | 城区部分老旧供水管网因已审批方案的人行道位置已被其他管线占用，需进行规划调整的部分较多，导致增加造价，影响施工进度。 | 钦州市开投水务有限公司 | 黄海波（项目负责人）13877779006、 周俊宏18377756820、王朝璋17772069119（现场代表） | 市城管执法局
3 | 钦州市河东污水处理厂二期工程 | 续建 | 新扩建日处理生活污水8.0万m³/d的生活污水处理设施。 主要建设内容为新建细格栅间及旋流沉砂池、改良A2O+MBBR池、配水井及污泥泵房、二沉池、气浮池配水井、高速离子气浮池、滤布滤池、紫外线消毒渠、贮泥池及污泥调理池等。 | 2021-2024 | 22700 | 6000 | 5193 |  | 5299 | 已完成第一批设备采购工作，已完成第二批设备采购招标工作。完成进水在线检测间主体结构施工；完成滤布滤池设备安装20%；完成紫外线消毒渠装饰装修施工；完成配电房砌筑、钢结构安装；完成中水回用加药间主体结构施工等。 | 由于本项目采用EPC工程总承包模式，用初步设计图纸进行招标，市财政评审中心只审核一次，施工图与初步设计图纸有出入，涉及到造价变动。 | 钦州市开投水务有限公司 | 李英（现场代表）15777739911 | 市城管执法局
4 | 钦州市水务综合提升项目 | 续建 | 1、水厂改扩建工程：优化钦州市第二水厂一期工程，在一期絮凝沉淀池进水管增加管式静态混合器 1 座；对二期工程进行技术改造，包括配水井建设、设备及工艺管道安装等；完善泥水处理系统，建设脱水机房、回用水池等泥水处理构筑物；根据现状及新建增加的设备，扩建完善原有电气系统、自控系统。钦州市第三水厂新增一套规模为3万m³/d 滤池处理系统，处理水厂原工业用水出水，将生活用水供水能力提高至5万m³/d。 2、供水管网建设工程：新建钦州市滨海新城片区环岛南路（北部湾大道至海岬1号路）、茶山江大街（滨海大道至扬帆大道）、嘉兴街（滨江东路至扬帆大道）等11条道路，共计约约40.27公里的供水管网、市政消防栓及相应的分区计量设备等。管径为DN250~DN500mm球墨铸铁管(K9级)。 3、钦州市智慧水务：（1）智慧水务应用架构类项目；（2）智慧水务数据资源架构项目；（3）智慧水务基础设施架构类项目；（4）智慧水务公司专项类项目。 | 2022-2024 | 21541.9 | 1000 | 191.99 |  | 524 | 供水管网建设： 前期工作：已完成； 项目进展：正在筹备施工工作； 水厂改扩建工程： 前期工作：第二水厂已经获得工程规划许可证，正在办理施工许可证；三水厂改扩建工程已完成前期手续； 项目进展：水厂改扩建工程本月完成石灰系统及虹吸滤池主体工程，本月完成虹吸滤池内外瓷砖铺贴工程，完成总平部分工艺管道施工；完成屋面防水工程，完成V型滤池砌筑工程等。 钦州市智慧水务： 前期工作：已取得初步设计批复。目前第一期建设方案上报集团公司通过审批，正在进行招标相关工作。 | 第二水厂扩建工程建设项目用地问题已对接资产公司，资产公司答复现已口头通知租户搬迁，具体时间还在商定。 | 钦州市开投水务有限公司 | 黄海波（项目负责人）13877779006、 王朝璋（供水管网建设工程）17772069119、 关家裕（水厂改扩建）18707777528 | 市城管执法局
5 | 钦州市生活垃圾处理场渗滤液处理站浓缩液处理工程项目 | 新建 | 对钦州市生活垃圾场渗滤液处理站产生的浓缩液进行净化处理，改善渗滤液处理站及周边库区的工作环境，防止垃圾渗滤液对周边环境产生污染，改善环境质量，建设日处理量100吨的浓缩液处理站一座。 | 2023-2024 | 3000 | 500 | 0 |  | 0 | 完成初步技术方案编制。 | 该项目未确定资金来源 | 钦州市环境卫生管理处 | 蓝琨珺19127730186 | 市城管执法局
6 | 钦州市生活垃圾处理场综合整治项目二期 | 续建 | 主要建设有害垃圾收集暂存点项目、大件垃圾处理中心项目、市城区生活垃圾转运站提升项目、市垃圾渗滤液处理项目。 | 2021-2024 | 2950 | 2100 | 1753 | 2021.8 | 500 | 已完成压缩设备采购，完成建安、梅园、德营、水东垃圾转运站设备提升改造。 | 该项目2022年以来作为债券项目进行储备，但多次尽调后，财政厅认为该项目设备占比大，因此将该项目列为需求库，目前还未获得发行。 | 钦州市环境卫生管理处 | 蓝琨珺19127730186 | 市城管执法局
|  |  |  | 6 | 120637.9 | 15600

## 资金 (hidden)
表2：
钦州市2020年总投资1000万元以上项目汇总表 （按资金来源分）
单位：万元
序号 | 单位名称 | 项目 个数 | 总投资 | 到2019年底累计完成投资 | 2020年计划投资 | 1-10月完成投资合计 | 完成进度 | 政府投资项目 | [6 empty] | 企业投资项目
[8 empty] | 个数 | 总投资 | 到2018年底累计完成投资 | 年度计划投资 | 投资占比 | 1-10月完成投资 | 完成进度 | 个数 | 总投资 | 到2018年底累计完成投资 | 年度计划投资 | 投资占比 | 1-10月完成投资 | 完成进度
合计 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
一 | 县区及园区管委 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1 | 灵山县人民政府 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 | 浦北县人民政府 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 | 钦南区人民政府 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
4 | 钦北区人民政府 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 | 钦州港区管委 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 钦州港区管委（含双牵头） | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 | 三娘湾旅游管理区管委 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | 中马钦州产业园区管委 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 | 钦州保税港区管委 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
9 | 钦州高新区管委 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
10 | 市滨海新城管委 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 市滨海新城管委（含双牵头） | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
11 | 市北部湾华侨投资区管委 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
二 | 双牵头部门 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
12 | 钦南区人民政府、钦北区人民政府 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
13 | 钦州高新区管委、钦南区人民政府 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
14 | 市住建局、钦南区人民政府、钦北区人民政府 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
15 | 市交通运输局、钦南区人民政府 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
16 | 市石化局、钦州港区管委 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
17 | 市城市管理行政执法局、钦南区人民政府、钦北区人民政府 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
18 | 市城市管理行政执法局、钦南区人民政府 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
19 | 市城市管理行政执法局、钦北区人民政府 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 市交通运输局、钦南区人民政府、钦北区人民政府 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
20 | 自治区北部湾港口管理局钦州分局、钦州港区管委 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
21 | 市交通运输局、钦州港区管委 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 市铁建办、中马钦州产业园区管委 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
22 | 市教育局、市滨海新城管委 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
23 | 市委党校、市滨海新城管委 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
三 | 市直部门及有关单位 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
24 | 市发改委 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
25 | 市交通运输局 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
26 | 自治区北部湾港口管理局钦州分局 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
27 | 市卫健委 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
28 | 市石化局 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
29 | 市城市管理行政执法局 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 钦州供电局 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
30 | 市水利局 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
31 | 市工信局 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
32 | 市科技局 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 市林业局 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 市土地储备中心 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 市食品药品监管局 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
33 | 市公安局 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
34 | 市人社局 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 钦州学院 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 市旅发委 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 市教育局 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 钦州市公安消防支队 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
35 | 市农业农村局 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 市口岸办 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
36 | 市人防海防办 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
37 | 市住建局 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
四 | 平台公司 | [5 empty] | #DIV/0! | [6 empty] | #DIV/0! | [6 empty] | #DIV/0!
| 市开投集团公司 | [5 empty] | #DIV/0! | [6 empty] | #DIV/0! | [6 empty] | #DIV/0!
| 市开投集团公司 |  |  |  |  | 0 | #DIV/0! | [6 empty] | #DIV/0! | [6 empty] | #DIV/0!
| 钦州恒远交通投资有限公司 |  |  |  |  | 0 | #DIV/0! | [6 empty] | #DIV/0! | [6 empty] | #DIV/0!
| 钦州市建恒森林建设投资有限公司 |  |  |  |  | 0 | #DIV/0! | [6 empty] | #DIV/0! | [6 empty] | #DIV/0!
| 钦州市旅游投资有限公司 |  |  |  |  | 0 | #DIV/0! | [6 empty] | #DIV/0! | [6 empty] | #DIV/0!
| 市滨海置业集团公司 |  |  |  |  | 0 | #DIV/0! | [6 empty] | #DIV/0! | [6 empty] | #DIV/0!
| 钦州临海工业公司 |  |  |  |  | 0 | #DIV/0! | [6 empty] | #DIV/0! | [6 empty] | #DIV/0!
| 其他园区及市直部门 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## 县区台账 (hidden)
2019年1— 月钦州市投资和重大项目建设工作台账（分县区园区）
| 隐藏 | [14 empty] | 隐藏 |  |  |  |  | 隐藏 |  |  |  |  | 隐藏 |  |  |  |  | 隐藏 |  |  |  | 隐藏 |  | 隐藏 |  | 金额单位：亿元
地 区 | 统计用地区名称 | 列入市级层面统筹推进重大项目情况 | [36 empty] | 1- 月完成投资快报
|  | 投资完成情况（亿元） |  |  | 项目开工情况（个） |  |  |  | 项目竣工情况（个） |  |  |  | 项目用地情况（亩） |  |  |  |  | 项目用林情况（亩） |  |  |  |  | 项目用海情况（亩） |  |  |  |  | 项目征拆情况（亩） |  |  |  |  | 项目融资情况（亿元） | [5 empty] | 总量 | 同比增长（%）
|  | 年度计划投资 | 累计完成投资 | 完成进度（%） | 计划开工 | 累计开工 | 开工率（%） | 未按计划开工 | 计划竣工 | 累计竣工 | 竣工率（%） | 未按计划竣工 | 项目数 | 实际用地需求 | 已落实用地 | 已落实用地 | 缺口 | 项目数 | 实际用林需求 | 已落实用林 | 已落实用林 | 缺口 | 项目数 | 实际用海需求 | 已落实用海 | 已落实用海 | 缺口 | 项目数 | 涉及征拆 | 已落解决 | 已落解决 | 未解决 | 项目数 | 年度计划投资 | 年度计划投资 | 已落实资金 | 已落实资金 | 资金缺口
总计 |  | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | 0 | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF! | #REF!
一、县区 |  | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
钦州港区 | 钦州港区管委 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
钦南区 | 钦南区人民政府 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
钦北区 | 钦北区人民政府 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
灵山县 | 灵山县人民政府 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
浦北县 | 浦北县人民政府 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
二、园区 |  | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
中马园区 | 中马钦州产业园区管委 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
钦州保税港区 | 钦州保税港区管委 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
高新区 | 钦州高新区管委 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
滨海新城 | 市滨海新城管委 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
华侨投资区 | 市北部湾华侨投资区管委 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
三娘湾管理区 | 三娘湾旅游管理区管委 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
三、市直部门 |  | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
市发改委 | 市发改委 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
市交通运输局 | 市交通运输局 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
自治区北部湾港口管理局钦州分局 | 自治区北部湾港口管理局钦州分局 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
市住建局 | 市住建局 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
市城市管理行政执法局 | 市城市管理行政执法局 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
市水利局 | 市水利局 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
市工信局 | 市工信局 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
市科技局 | 市科技局 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
市卫健委 | 市卫健委 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
市公安局 | 市公安局 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
市教育局 | 市教育局 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
市农业农村局 | 市农业农村局 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
市人防海防办 | 市人防海防办 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
四、双牵头部门 |  | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
钦南区、钦北区 | 钦南区人民政府、钦北区人民政府 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
高新区、钦南区 | 钦州高新区管委、钦南区人民政府 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
市住建局、钦南区、钦北区 | 市住建局、钦南区人民政府、钦北区人民政府 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
市交通运输局、钦南区 | 市交通运输局、钦南区人民政府 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
市城市管理行政执法局、钦南区人、钦北区 | 市城市管理行政执法局、钦南区人民政府、钦北区人民政府 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
市城市管理行政执法局、钦南区 | 市城市管理行政执法局、钦南区人民政府 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
市城市管理行政执法局、钦北区 | 市城市管理行政执法局、钦北区人民政府 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
自治区北部湾港口管理局钦州分局、钦州港区 | 自治区北部湾港口管理局钦州分局、钦州港区管委 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
市石化局、钦州港区 | 市石化局、钦州港区管委 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
市交通运输局、钦州港区 | 市交通运输局、钦州港区管委 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
市教育局、滨海新城 | 市教育局、市滨海新城管委 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
市委党校、滨海新城 | 市委党校、市滨海新城管委 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## 行业台账 (hidden)
2019年1— 月钦州市投资和重大项目建设工作台账（分行业）
| 隐藏 | [14 empty] | 隐藏 |  |  |  |  | 隐藏 |  |  |  |  | 隐藏 |  |  |  |  | 隐藏 |  | 隐藏 |  |  |  | 隐藏 |  | 金额单位：亿元
行 业 | 统计用行业名称 | 列入市级层面统筹推进重大项目情况 | [36 empty] | 1- 月完成投资快报
|  | 投资完成情况（亿元） |  |  | 项目开工情况（个） |  |  |  | 项目竣工情况（个） |  |  |  | 项目用地情况（亩） |  |  |  |  | 项目用林情况（亩） |  |  |  |  | 项目用海情况（亩） |  |  |  |  | 项目征拆情况（亩） |  |  |  |  | 项目融资情况（亿元） | [5 empty] | 总量 | 同比增长（%）
|  | 年度计划投资 | 累计完成投资 | 完成进度（%） | 计划开工 | 累计开工 | 开工率（%） | 未按计划开工 | 计划竣工 | 累计竣工 | 竣工率（%） | 未按计划竣工 | 项目数 | 实际用地需求 | 已落实用地 | 已落实用地 | 缺口 | 项目数 | 实际用林需求 | 已落实用林 | 已落实用林 | 缺口 | 项目数 | 实际用海需求 | 已落实用海 | 已落实用海 | 缺口 | 项目数 | 涉及征拆 | 已落解决 | 已落解决 | 未解决 | 年度计划投资 | 项目数 | 年度计划投资 | 已落实资金 | 已落实资金 | 资金缺口
总计 |  | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
一、工业 | 工业 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
二、交通 |  | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1.公路 | 公路 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2.水运 | 水运 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3.铁路 | 铁路 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
三、市政设施 |  | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1.城市路网 | 城市路网 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2.其他市政设施 | 其他市政设施 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
四、房地产
五、商贸流通 | 商贸流通 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
六、社会事业 |  | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1.教育 | 教育 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2.卫生 | 卫生 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3.文化 | 文化 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
七、农林水牧渔 |  | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1.农业 | 农业 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2.林业 | 林业 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3.水利 | 水利 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
4.畜牧业+渔业 | 牧渔业 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
八、其他 | 其他 | #REF! |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[13 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!